## Summary
“Found By” Classification | Count | Note
Simulation | 18 | Sum of sub-classifications below
Inspection | 13 | Confidence in this classification is low – few issues explicitly stated that they were found by inspection
Formal Verification | 13 | This includes both Designer and Verifier use of FV
Lint | 2
Unknown | 1
Simulation sub-classifications | Count | Note
Directed, self checking test | 10 | Many directed tests supplied by Designers and a couple by the Open Source Community at large
Step & Compare | 6
corev-dv | 2 | Simulation with corev-dv also uses step & compare
Type | Count | Note
RTL functional | 40
RTL coding style | 4 | Linter issues, removing TODOs, removing `ifdefs, etc.
Non-RTL functional | 1
Unreproducible | 1
Invalid | 1

## review
Filter: | is:issue created:>2020-02-27
Issue # | Title | Type | Resolution | Found By | Notes
258 | VCS fails to compile correctly | RTL coding style | Fixed | Simulation (directed)
293 | Possible inferred latches in riscv_pmp.sv | RTL coding style | Waived | Lint | 1. “Lint” tool was dsim 2. File renamed to cv32e40p_pmp.sv 3. PMP feature not supported in v1.0.0 release
306 | Exception Controller in CSR loads wrong mpp on MRET | RTL functional | Waived | Inspection | Axiomise. Why was this waived? Looks fixed to me...
308 | Code not running with fpnew in verilator | RTL coding style | Waived | Simulation (directed) | Why was this waived? Should be closed.
329 | tracer out of order for half-word aligned fence.i | Non-RTL functional | Closed | Simulation (step&compare) | Typically a bug in Tracer/Wrapper
362 | p.elw instruction should be legal only in PULP_CLUSTER | RTL functional | Closed | Simulation (directed)
363 | Wrong (none) bypass usage by pv.cplxconj | RTL functional | Closed | Simulation (directed)
372 | pv.cplxconj decoding and tracing | RTL functional | Closed | Inspection
378 | Vectored interrupt changes ? | Invalid | Closed | Simulation (step&compare) | Closed issue as it either has been fixed, or because it is no longer valid.
381 | Non-standard CSRs | RTL functional | Closed | Inspection
392 | Possible ISA incompliance in PMP | RTL functional | Waived | Unknown | PMP feature not part of v1.0.0 release
404 | Missed debug_req_i pulse | RTL functional | Closed | Formal Verification | SiLabs
406 | Re-introduce Hardware Loop functionality | RTL functional | Closed | Inspection | Not a “bug”, a feature re-introduction.
418 | Simultaneous request of debug, trigger, and interrupt | RTL functional | Closed | Formal Verification | SiLabs
424 | Missing case select item (csr_save_ex_i) | RTL coding style | Closed | Lint | Lint issue (probably not functional, but worth fixing).
427 | Security hole in hardware loop, sketch of a possible mitigation | RTL functional | Waived | Inspection | HWLP not supported in v1.0.0 release
428 | several possible PMP nonconformances? | RTL functional | Waived | Inspection | PMP feature not supported in v1.0.0 release
429 | HPM counter logic 'possibly' not implemented correctly | RTL functional | Closed | Inspection
430 | Fix TODOs in RTL | RTL functional | Closed | Inspection | Not all of these will be bugs (maybe none are).
434 | taken bge followed by div takes 36 cycles | RTL functional | Closed | Simulation (step&compare)
438 | Illegal Instruction Exception not Raised - URET | RTL functional | Closed | Formal Verification | OneSpin
439 | Illegal Instruction Exception Raised Incorrectly – C.EBREAK | RTL functional | Closed | Formal Verification | OneSpin
440 | Illegal Instruction Exception Raised Incorrectly – CSRs | RTL functional | Closed | Formal Verification | OneSpin
441 | Illegal Instruction Exception Raised Incorrectly – MRET | RTL functional | Closed | Formal Verification | OneSpin
442 | Illegal Instruction Exception Raised Incorrectly - FENCE | RTL functional | Closed | Formal Verification | OneSpin
443 | Incorrect DCSR value read/ written | RTL functional | Closed | Formal Verification | OneSpin
445 | Stepie bit in DCSR not implemented | RTL functional | Closed | Simulation (step&compare)
448 | mcounteren CSR should not exist | RTL functional | Closed | Inspection | Response to change in RISCV ISA
449 | Retracted interrupt can cause instructions to be skipped | RTL functional | Closed | Simulation (directed)
452 | Some of the Xpulp instructions use reserved/standard opcodes | RTL functional | Open | Inspection | Only impacts PULP_XPULP, which is not supported in v1.0.0
457 | Opcodes marked as reserved should be avoided ... | RTL functional | Duplicate | Formal Verification | Axiomise
460 | interrupt CSR checks fail when interrupt occurs during div instruction | RTL functional | Closed | Simulation (step&compare) | SteveR
462 | Hardware Loop assertion fires | RTL functional | Waived | Formal Verification | 1. SiLabs 2. Only impacts PULP_XPULP, which is not supported in v1.0.0
466 | Instruction after stalled load retires out of order | RTL functional | Wont Fix | Simulation (directed) | Not a bug – by design
467 | cs_registers_i.a_single_step is not covered during Formal | Unreproducible | Closed | Formal Verification | SiLabs
490 | Debug Mode : dpc contains wrong value after dret to trigger match address==data2 | RTL functional | Closed | Simulation (step&compare)
496 | The step or resume operation is error(depc error) when the SW/HW bp is set in a J instruction | RTL functional | Closed | Simulation (directed) | Same root cause as #490
498 | Wrong result from lw instruction | RTL functional | Closed | Simulation (directed) | Out of date version of the RTL (bug was fixed by the time this was reported)
503 | interrupt handler entry after CSRRC instruction clears local interrupt | RTL functional | Closed | Simulation (corev-dv) | SteveR
509 | Core executes wrong instruction | RTL functional | Closed | Formal Verification | OneSpin
529 | Wrong dcsr.cause after sleep | RTL functional | Closed | Simulation (corev-dv) | OysteinK’
533 | Illegal Instruction Retires | RTL functional | Closed | Formal Verification | OneSpin
540 | Performance counter retired instruction count error | RTL functional | Closed | Simulation (directed)
563 | CV32E40P does not signal signal 'halted', 'running', 'havereset' to the Debug Module | RTL functional | Closed | Inspection | Change of specification (User Manual)
571 | Single stepping through hwloop does not work | RTL functional | Waived | Simulation (directed) | Only impacts PULP_XPULP, which is not supported in v1.0.0
583 | HWLoop minimum size 3 illegal exception | RTL functional | Waived | Inspection | Only impacts PULP_XPULP, which is not supported in v1.0.0
585 | Bug in PMP register region bound checking | RTL functional | Waived | Inspection | Only impacts PMP, which is not supported in v1.0.0